## Sheet1
|  |  | October |  | November |  |  |  | December |  |  |  |  | January
Task Name | Duration (Weeks) | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2018-01-07 | 2018-01-14 | 2018-01-21 | 2018-01-28
DEVELOPMENT
Brainstorming | 1
Narrative Story writing | 2
Concept Art and Research | 2
PRODUCTION
2D Element Design | 6
3D Modeling | 8
Map Design | 3
Flash Menu Integration | 3
UV Mapping and Texture Design | 8
Motion Graphics and Video Integration | 3
Sound Production | 3
Sound Recording | 1
Unreal Editor Integration | 2
Play Testing | 3